## RMS
Screen/Function | Description | Level | LOC | Planned-In | In Charge | Done-In | RDS | Status | Updated | Update Details | Note
Login System | As a user with a specific role, I want to be redirected to the appropriate page after login so that I can immediately access the features relevant to my role. | Level 1 | 60 | Iteration 1 |  | Iteration 1 | II.1.3, III.5 | To Do | Not Yet
Register User Account | As a new user, I want to register an account with my full name, email, and password so that I can access the features of the system. | Level 1 | 60 | Iteration 1 |  | Iteration 1 | II.2.1; III.1.1.a | To Do | Not Yet
List All Rooms | As a guest or customer, I want to view a list of all available rooms so that I can explore my options before filtering or searching. | Level 1 | 60 | Iteration 1 |  | Iteration 1 | II.1.2, III.1.2 | To Do | Not Yet
View Room Detail | As a guest, I want to view detailed information for a specific room so that I can make an informed booking decision. | Level 1 | 60 | Iteration 1 |  | Iteration 1 | II.1.4, III.1.3 | To Do | Not Yet
Search Room | As a guest, I want to search for rooms by location, date, and number of guests so that I can find a suitable place to stay. | Level 1 | 60 | Iteration 1 |  | Iteration 1 | II.1.1, III.1.1.b | To Do | Not Yet
Change Password |  | Level 1 | 60 | Iteration 1 |  | Iteration 2 |  | To Do | Not Yet
Blogs List |  | Level 1 | 60 | Iteration 2 |  | Iteration 2 |  | To Do | Not Yet
Blog Details |  | Level 1 | 60 | Iteration 2 |  | Iteration 2 |  | To Do | Not Yet
Posts List |  | Level 1 | 60 | Iteration 2 |  | Iteration 2 |  | To Do | Not Yet
Post Details |  | Level 1 | 60 | Iteration 2 |  | Iteration 3 |  | To Do | Not Yet
Setting List |  | Level 1 | 60 | Iteration 3 |  | Iteration 3 |  | To Do | Not Yet
Setting Details |  | Level 1 | 60 | Iteration 3 |  | Iteration 3 |  | To Do | Not Yet
Users List |  | Level 1 | 60 | Iteration 3 |  | Iteration 3 |  | To Do | Not Yet
User Details |  | Level 1 | 60 | Iteration 3 |  | Iteration 3 |  | To Do | Not Yet
Note on C1: KienNT: Complexity Levels Level 1: 3-5 fields OR 2 trans Level 2: 6-7 fields OR 3 trans Level 3: 8-9 fields OR 4 trans Level 4: 10-11 fields OR 5 trans Level 5: 12-13 fields OR 6 trans Level 6: 14-15 fields OR 7 trans Level 7: >15 fields OR >7 trans
Note on E1: kiennt: Kế hoạch sẽ làm trong iteration nào?
Note on G1: kiennt: Thực tế đã làm xong trong iteration nào?
Note on H1: KienNT: Phân tích yêu cầu và thiết kế cho màn hình/chức năng được mô tả trong phần nào của tài liệu RDS?
Note on J1: kiennt: Chức năng đã được update/bổ sung trong iteration nào sau khi được review
Note on K1: kiennt: Các nội dung update cụ thể, mô tả theo định dạng sau: dd/MMM-AccountName: Abc Xyz - dd/MMM: ngày thực hiện update (ví dụ 13/Oct) - AccountName: tài khoản của SV đã thực hiện update (ví dụ KienNT hoặc KienNTHe171209) - Abc Xyz: mô tả nội dung update
Note on C2: KienNT: Level 1: 3-5 fields OR 2 trans Level 2: 6-7 fields OR 3 trans Level 3: 8-9 fields OR 4 trans Level 4: 10-11 fields OR 5 trans Level 5: 12-13 fields OR 6 trans Level 6: 14-15 fields OR 7 trans Level 7: >15 fields OR >7 trans

## Params
Screen/Function Complexity Levels
Screen complexity can be defined based on the screen's fields OR screen/function's transactions | Level | Fields | Trans* | LOC | Notes
- Transactions can be counted as number of transactions to the database or external systems/subsystems | Level 1 | 3-5 | 2 | 60 | 3-5 fields OR 2 trans
- Fields are screen's actionable components or database table fields; if there are some transactions those are | Level 2 | 6-7 | 3 | 90 | 6-7 fields OR 3 trans
not "related" to any fields, each of those transactions are counted as two fields and add those extra number | Level 3 | 8-9 | 4 | 120 | 8-9 fields OR 4 trans
to the total number of fields to define the screen/function complexity | Level 4 | 10-11 | 5 | 150 | 10-11 fields OR 5 trans
| Level 5 | 12-13 | 6 | 180 | 12-13 fields OR 6 trans
Some samples of screen complexity defining are as following | Level 6 | 14-15 | 7 | 210 | 14-15 fields OR 7 trans
Sample #1 | Level 7 | >15 | >7 | 240 | >15 fields OR >7 trans
*One trans (transactions) = Two fields (actionable screen components)
Sample #2
Sample #3